## Risk log
Risk Log: Buckinghamshire Local Enterprise Partnership | [5 empty] | Date of last update: 6.11.20 By: RH/IB
Risk Detail | [5 empty] | Risk Assessment |  |  |  | Mitigation
Ref. | Date | Review | Raised by | Owner | Description | Likelihood | Impact | Overall Severity | Change Since September20 | Mitigating Action or Controls | Closed | Internal/External
1 | 2020-01-29 | 28.4.20 | Board | RH/AS | Dissolution of LEPs due to weakening relationship with Government and certainty of capital and revenue funding. | 1 | 4 | 4 | No Change | Maintain close relatinships with MP's & LEP Network. Ensure delivery against Government targets through Annual Performance Review. Ensure that reserve balances are sufficient to maintian delivery independently. Ensure delivery of Getting Building Programme on schedule. | No | External
2 | 2020-01-29 | 28.4.20 | Board | RH/IB | Potential division of Economic priorities leading to reduced investment in Buckinghamshire Economic Assets and Drivers | 3 | 4 | 12 | No Change | Importance of supporting a strong and aligned Buckinghamshire Devolution Proposal and strong business representation within Buckinghamshire Growth Board, ensuring that communication channels are strengthened with national Government partners and maintained with neighbouring LEPs | No | Internal
3 | 2020-01-29 | 28.4.20 | Board | RH | Failure to implement Local Industrial Strategy due to prioritisation, structure and or insufficient resource. | 2 | 5 | 10 | No Change | Advisory panel and delivery sub-board structure implemented, board approval to support team delivery resilience. Increased risk due to short term focus on COVID 19 Emergency Activities. LIS delivery positioned as part of Recovery Programme. Likely announcement in early 2021 re new Local Industrial Strategy process | No | Internal
4 | 2020-01-29 | 28.4.20 | Board | RH/AS/MT | Duplication of economic activity with Buckinghamshire Council. | 1 | 4 | 4 | No Change | Ensure close working relationship with senior executive officers and members of the new authority. Ensure all members are aware of the impact of LEP supported services. Good working relationship established as part of Recovery Programme, needing to be maintained as new BC team appointed. | No | Internal
5 | 2020-01-29 | 28.4.20 | Board | RemNom Sub Group | Failure to comply with natioinal guidelines on board diversity. Board member recruitment. Characteristics, capacity, diversity and capability on the Board to be in line with the LEP Review. | 2 | 3 | 6 | No change | Terms of reference of RemNom committee to ensure board membership reflects appropriate diversity and skills needs for Buckinghamshire. HR suport now provided by independent agency. Board recruitment for vacant posts underway, gender diversity at forefront of selectino criteria. | No | Internal
6 | 2020-01-29 | 28.4.20 | Board | RH/PB | Failure to complete of MOU and complete successful implementation of agreement with BBF over finance, HR and data security. Capacity of LEP to deliver on its obligations while maintaining operationally robust and secure systems and procedures. | 2 | 3 | 6 | No Change | Weekly operational meetings arranged between LEP & BBF Executive Teams - continuation of daily meetings ongoing in remote working operation . | No | Internal
7 | 2020-01-29 | 28.4.20 | Board | JR | Reputational damage to BLEP as a result of strategic/delivery partner failure/position. | 4 | 4 | 16 | No Change | Quarterly meetings with all project sponsors, contract agreement ensures partners notify LEP of any major change to LGF programme delivery schedule. Risk increased due to Covid 19 Business Conditions and repayment schedule requests. | No | External
8 | 2020-01-29 | 28.4.20 | Board | JR | Failure to achieve full and total spend on LGF programme by March 2021. | 3 | 4 | 12 | No Change | Quarterly meetings with all project sponsors, contract agreement ensures partners notify LEP of any major change to LGF programme delivery schedule. | No | Internal
9 | 2020-01-29 | 28.4.20 | Board | RH | Failure to secure funding to run ancillary programmes such as growth hub, skills team, Enterprise Zone and BA | 2 | 4 | 8 | No change | Ensure all Government programme support submissions are met and ensure that reserves allow for core services to be delivered for 3 months following any loss of funding. Core Growth Hub Funding for current year secured. Need to ensure impact of CSR delay is managed and that reserve funding is suitable for any funding delays. | No | External
10 | 2020-01-29 | 28.4.20 | Board | RH/AS | Failure to Secure Aylesbury Woodlands planning promotion and Eastern Link Road delivery. | 4 | 4 | 16 | No Change | Continued Executive Participation in Woodlands Stakeholder Board. Board Representation on BA Management Board. Date now agreed for Planning Committee February 2021 | No | External
11 | 2020-07-30 | 30.7.20 | Board | Rem Nom Sub Group | Unplanned Loss of key member of Executive or Board | 4 | 3 | 12 | Decrease | Ensure close team collaboration, mentoring & role shadowing. Ensure operational resilience reviews are undertaken to ensure information is accessible to multiple individuals and that operational processes are resilient to absence of individual team member. | No | Internal
12 | 27.11.20 | 22.11.20 | Finance & Audit Sub Group | RH/PB | Non delivery by BBF Growth Hub service | 1 | 4 | 4 | N/A | Existing Growth Hub delivery contract, to be supplemented by MOU to confirm operational relationship and BBF/LEP delivery commitments. | No | Internal
[6 empty] | 0 | 0 | 110 | Decrease from September
[6 empty] | 0 | 0 | 110/300 | Overall Risk for the LEP
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
KEY
Likelyhood and Impact graded 1-5
0-9
10 to 15
16 And Above
Overall Impact for the Company
0-40% overall risk
40%-60% overall risk
Above 60% overal risk